## Project-Management-Sample-Data(
Excel Sample Data
Project Management Data
| Task Name | Assigned to | Start Date | Days Required | End Date | Progress
Marketing | Market Research | Alice | 2024-01-01 | 13 | 1/14/2024 | 78%
Marketing | Content Creation | Bob | 1/14/2024 | 14 | 1/28/2024 | 100%
Marketing | Social Media Planning | Charlie | 1/28/2024 | 22 | 2/19/2024 | 45%
Marketing | Campaign Analysis | Daisy | 2/18/2024 | 25 | 3/14/2024 | 0%
Product Dev | Prototype Development | Ethan | 2024-02-01 | 18 | 1/20/2024 | 100%
Product Dev | Quality Assurance | Fiona | 1/20/2024 | 10 | 1/30/2024 | 78%
Product Dev | User Interface Design | Gabriel | 2024-04-02 | 25 | 2/29/2024 | 0%
Customer Svc | Service Improvement | Hannah | 2024-01-02 | 22 | 2/23/2024 | 100%
Customer Svc | Ticket Resolution | Ian | 2/24/2024 | 25 | 3/20/2024 | 100%
Customer Svc | Customer Feedback | Julia | 3/21/2024 | 30 | 4/20/2024 | 0%
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2/24/2024 | 10%
Financial | Financial Reporting | Mark | 2/13/2024 | 21 | 2024-09-02 | 78%
Financial | Investment Planning | Mark | 3/19/2024 | 25 | 4/13/2024 | 100%
Research | Market Trends Analysis | Nathan | 2024-02-01 | 23 | 1/25/2024 | 50%
Research | Data Collection | Olivia | 1/26/2024 | 32 | 2/27/2024 | 0%
Research | Research Paper Writing | Peter | 2/28/2024 | 27 | 3/26/2024 | 0%
Development | Software Development | Quinn | 2024-02-01 | 36 | 2024-07-02 | 100%
Development | Feature Enhancement | Rachel | 2024-08-02 | 34 | 3/13/2024 | 0%
Development | Code Review | Sam | 3/14/2024 | 30 | 4/13/2024 | 0%
Production | Manufacturing | Tim | 2024-03-01 | 47 | 2/19/2024 | 30%
Production | Quality Control | Ursula | 2/17/2024 | 27 | 3/15/2024 | 0%
Production | Packaging Design | Victor | 3/14/2024 | 22 | 2024-05-04 | 0%
Sales | Lead Generation | Wendy | 2024-03-01 | 60 | 2024-03-03 | 70%
Sales | Client Meetings | Xavier | 2024-06-01 | 20 | 1/26/2024 | 78%
Sales | Contract Negotiation | Yvette | 2024-03-02 | 35 | 2024-09-03 | 0%
Support | Technical Support | Zoe | 2024-01-01 | 25 | 1/26/2024 | 100%
Support | Bug Fixes | Aaron | 1/27/2024 | 31 | 2/27/2024 | 100%
Support | Software Updates | Bella | 2024-02-03 | 22 | 3/24/2024 | 0%
Operations | Process Optimization | Calvin | 2024-03-01 | 30 | 2024-02-02 | 40%
Operations | Inventory Management | Diane | 2024-03-02 | 25 | 2/28/2024 | 0%
Operations | Facility Maintenance | Edward | 2/29/2024 | 20 | 3/20/2024 | 0%
Consulting | Strategic Planning | Fiona | 2024-02-01 | 35 | 2024-06-02 | 60%
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-05-03 | 0%
Consulting | Client Advisory | Helen | 2024-06-03 | 25 | 3/31/2024 | 0%
Training | Employee Training | Isaac | 2024-04-01 | 27 | 1/31/2024 | 80%
Training | Certification Programs | Jane | 1/28/2024 | 30 | 2/27/2024 | 0%
Training | Skill Development | Kyle | 2/28/2024 | 22 | 3/21/2024 | 0%
Events | Event Planning | Laura | 2024-03-01 | 25 | 1/28/2024 | 30%
Events | Conference Management | Mike | 2024-03-02 | 20 | 2/23/2024 | 0%
Events | Sponsorship Coordinatio | n Nancy | 2/24/2024 | 35 | 3/30/2024 | 0%
Logistics | Supply Chain Management | Oscar | 2024-03-01 | 25 | 1/28/2024 | 50%
Logistics | Transportation Planning | Patricia | 1/29/2024 | 30 | 2/28/2024 | 100%
Logistics | Inventory Optimization | Quentin | 3/29/2024 | 20 | 4/18/2024 | 0%
Engineering | Product Design | Rachel | 2024-02-01 | 25 | 1/27/2024 | 20%
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2/24/2024 | 0%
Engineering | Prototype Testing | Tom | 2/23/2024 | 27 | 3/21/2024 | 0%